## New EHCP
NEW EHC PLAN — 20-WEEK STATUTORY TIMELINE TRACKER
STEP 1 — Enter the date the LA received the request for an EHC needs assessment: |  |  | 2027-02-19 | <- EXAMPLE date - replace with your own |  |  | Prepared by Justify Foundation
Optional — Date the DRAFT plan was actually received (refines the 15-day response deadline): | [6 empty] | Tool provided free without obligation or liability
How to use: | Enter dates ONLY in the yellow cells. All deadline dates calculate automatically. 'Status' compares today's date and any actual date you record against the statutory deadline.
Colour key: | LA must act | Parent / young person acts | School acts | Joint / all
Week / stage | Milestone / action | Who acts | Deadline (calculated) | Actual date (enter) | Status (auto) | Legal source | Notes
Week 0 | Request for EHC needs assessment received by the LA (clock starts). Parent, young person or school may request; anyone may bring the child to the LA's attention. | Parent | 2027-02-19 |  | Upcoming | CFA 2014 s 36(1), (3) | Send in writing; keep proof of the date of receipt.
Week 0+ | LA consults the parent, and notifies health, social care and the school that an assessment is being considered; notifies parent of right to submit views and evidence. | LA | 2027-02-19 |  | Upcoming | SEND Regs 2014 regs 3, 4(2); s 36(7) | 'As soon as practicable' - chase if nothing within days.
By week 2 (recommended) | Parent submits views, evidence and any private/NHS reports to feed the week-6 decision. | Parent | 2027-03-05 |  | Upcoming | s 36(7) | RECOMMENDED (not statutory) - earlier is better.
Week 6 | LA must notify its decision whether it will carry out the EHC needs assessment. | LA | 2027-04-02 |  | Upcoming | reg 5(1); test: s 36(8) | Test is 'MAY be necessary' - a low threshold. Exceptions: reg 5(4) only.
Week 6 + 2 months | If REFUSED: latest day to lodge appeal with the First-tier Tribunal (SEND). | Parent | 2027-06-02 |  | Upcoming | s 51(2)(a); HESC Rules 2008 r 20(1)(c) | 2 months from the ACTUAL decision letter, or 1 month from a mediation certificate if later - enter the real decision date in column E of the row above and recalculate accordingly.
Week 12 (latest, in practice) | All statutory advices returned: each adviser (school, medical, educational psychologist, social care, anyone the parent reasonably requests) must respond within 6 weeks of the request to them. | LA / Advisers | 2027-05-14 |  | Upcoming | regs 6(1), 8(1) | Date shown assumes requests sent at week 6. Parent may require extra advisers: reg 6(1)(h). Adviser exceptions: reg 8(2).
Week 16 | If the LA decides NOT to issue a plan, it must notify the parent by this date (with appeal rights). | LA | 2027-06-11 |  | Upcoming | reg 10(1), (3) | Appeal: s 51(2)(b); same 2-month / 1-month windows.
~Week 17 (practical) | Draft EHC plan issued. Section I (school) must be BLANK in the draft. | LA | 2027-06-18 |  | Upcoming | s 38; s 38(5) | No separate statutory date, but the draft must leave the 15-day window inside 20 weeks - chase if not received by ~week 17. Enter actual receipt date in D5 above.
Draft + 15 days | Parent's representations: comments on the draft, request for a particular school, and (optionally) a meeting with the LA. | Parent | 2027-07-03 |  | Upcoming | reg 13(1); s 38(2) | MINIMUM 15 days - runs from actual service of the draft (D5 if entered). Check Sections B and F are specific and quantified.
Draft + 15 days onwards | LA consults the requested school / other institution; school should respond within 15 days. | LA / School | 2027-07-09 |  | Upcoming | s 39(2); Code 9.83 | School's 15-day response is Code guidance, not statute. LA must name the school unless s 39(4) applies.
Week 20 | FINAL EHC plan must be issued and sent to parent, school and health. | LA | 2027-07-09 |  | Upcoming | reg 13(2); reg 14 | Only exceptions: reg 13(3)/10(4) (summer-closure advice requests; exceptional personal circumstances; 4+ weeks' absence). Caseload / EP shortage is NOT a lawful reason.
Week 20 | Duty to secure ALL Section F provision begins; named school must admit. | LA | 2027-07-09 |  | Upcoming | s 42(2); s 43(2) | Absolute, non-delegable duty - 'best endeavours' is not the test.
Final + 2 months | Latest day to appeal the CONTENT of the final plan (Sections B, F, I). | Parent | 2027-09-09 |  | Upcoming | s 51(2)(c); HESC r 20(1)(c) | 2 months from the ACTUAL final plan, or 1 month from mediation certificate if later - recalculate from the real issue date in column E two rows above.
If a deadline is missed
(1) chaser letter citing the exact regulation and date;
(2) formal complaint / LGSCO
(3) judicial review pre-action letter - delay is for the courts, not the Tribunal: R (W) v Hertfordshire CC [2023] EWHC 3138 (Admin); R (JSC) v Cambridgeshire CC [2026] EWHC 68 (Admin).
Sources: | legislation.gov.uk/uksi/2014/1530 ¦ legislation.gov.uk/ukpga/2014/6/part/3 ¦ gov.uk/government/publications/send-code-of-practice-0-to-25 ¦
Note | This tool and information provided is for guidance only and does NOT constitute legal advice.
Formulas:
Status (auto) = IF(OR([School acts]="",ISBLANK([School acts])),"",IF([Joint / all]<>"",IF([Joint / all]<=[School acts],"Met","Late"),IF(TODAY()>[School acts],"OVERDUE","Upcoming")))